## 1.Cover
TEST PLAN ¦ PROJECT: BBSoC - IP Viterbi
| Revision | : Rev1.4
| Prj Duration | : 09/2025 -
| Author | : Hienntt87 - Tuantqa
| Approval | : Phuongtv29

## 2.History_
HISTORY
Description
- The history is used for recording all modification of this document
- Please update exactly info to review correctly in the future
No | Date | Content | Updated by | Revision | Remark
1 | 2025-08-08 | - Create new | Hienntt87 | R0.1
2 | 15/8/2025 | - Create Milestone for IP Viterbi Decoder | Hienntt87 | R0.1
3 | 28/8/2025 | - Create Testplan for Convolution Encoder and Viterbi Decoder | Hienntt87 | R1.0
4 | 2025-05-09 | - Update Testplan for both Convolution Encoder and Viterbi Decoder | Hienntt87 | R1.1
5 | 2025-03-10 | - Update Testlist for Convolution Encoder | Hienntt87 | R1.2
6 | 21/11/2025 | - Update the result of test for encoder - Update version RTL, fix the bug of IP encoder | Hienntt87 | R1.3
7 | 28/1/2026 | - Update Testlist with newformat - Update version RTL - Add 2 sheet about scenario flow and sva_list | Hienntt87,Tuantqa | R1.4

## 3.Milestone
MILESTONE
Description
Based on requirement of customer, the milestone is created
| 2025-08-08 |  | 2025-08-22 |  |  | 2025-09-12 |  |  | 2025-10-01 |  |  | 2025-10-20 |  |  | 2025-10-03
|  |  |  | 2025-08-26 |  |  | 2025-09-17 |  |  | 2025-10-06 |  |  | 2025-10-23 |  |  | 2025-11-08
Start Prj
Phase 1: read document + a plan's verification
Release Ph1
Review Ph1
Phase 2: Setup UVM Environment
Release Ph2
Review Ph2
Phase 3: Pattern Gen + Verification Convolution Encoder
Release Ph3
Review Ph3
Phase 4: Pattern Gen + Verification Viterbi Decoder
Release Ph4
Review Ph4
Phase 5: Annotation Check
Release Ph5
Review Ph5
Review Final
End Project

## 4.Summary
SUMMARY REPORT
Description
- This sheet is used to collect and summarize all
results from other sub sheets
Summary Result
Status | Level | Revision | ENV revision | No. of planned items | No. of finished items | Remain | Remark
Done | RTL | v1.0.5 |  | 25 | 25 | 0 | Both Encoder and Decoder
Not yet | Pre-simulation |  |  | 0 | 0 | 0
Not yet | Post-simulation |  |  | 0 | 0 | 0
Note on C10: - Refer to Sheet 6.Testlist for detail
Note on D10: - Testbench revision, hash of ENV on repo

## 5.Testplan
TESTPLAN
Section | Check Item | Description | Test Name | Path | Type | Weight | Goal | Method | Owner | Assertion | Milestone | Design Status | Result | Environment | Note
1 | Convolution Encoder
1.1 | Reset
1.1.1 | Reset through axi bus | Verify data in internal register return the (default value) after trigger AXI_RST_N | test_encoder_read_reg_after_reset |  | Test | 1 | 100 | Directed | Hienntt87
1.1.2 | Reset when IP is performing encode | Trigger reset entire environment when performing encode, after trigger reset, the encoder re-start follow specification | test_encoder_trigger_reset_when_encoding_data |  | Test | 100 | 100 | Constraint Random | Hienntt87
1.2 | Register
1.2.1 | Convolution Encoder read/write internal register | Random read/write data of internal register to verify behavior RO/WO of each internal register | test_encoder_write_and_read_reg |  | Test | 1 | 100 | Constraint Random | Hienntt87
1.2.2 | Convolution Encoder valid range address | Write random data to reserved region address of each internal register to check behavior of IP to access that region - Checkpoint: Valid address of each interal registers | test_encoder_check_valid_range_address |  | Test | 100 | 100 | Constraint Random | Hienntt87
1.3 | AXI Protocol | [13 empty] | Burst read transaction over AXI are supported, but burst write transactions are not
1.3.1 | Axi Burst channel read | Change fields such as ARLENGTH, ARSIZE and ARBURST to verify behavior of read transaction when read data from Dbit Out Memory | test_encode_basic_directed_data / test_encode_directed_sweep_bit_1_data / test_encode_random_data / … |  | Coverpoint | 1 | 100 | Constraint Random | Hienntt87
1.3.2 | ID of both channel read and write | Change field ID when perform transaction read or write to check responed's ID | test_encode_basic_directed_data / test_encode_directed_sweep_bit_1_data / test_encode_random_data / … |  | Coverpoint |  | 100 | Constraint Random
1.4 | Convolution Encoder Functions
1.4.1 | Operation of Convolution Encoder | Perform normal operation with random data_in to encode - Checkpoint: Behavior of polling status of each register in dbit_out memory to identify encode completely done or not yet - Checkpoint: Format of axi_wdata when pass data_in to encode - Checkpoint: Random AW_ID and expected B_ID return the same value - Checkpoint: Random data input with 3 ranges, low-middle-high | test_encode_basic_directed_data / test encode_random_data / … |  | Test | 1000 | 100 | Constraint Random | Hienntt87
1.4.2 | Pattern Sweep with all bit 1/0, alternate 1/0, and walking 0/1 | Perform normal operation with special data_in to encode to check logic of XOR, shift register and polynomial taps | test_encode_directed_sweep_bit_1_data / test_encode_directed_alternative_bit_1_0_data / … |  | Test |  | 100 | Directed | Hienntt87
1.4.3 | Time to completely finish a encode process | Trigger start, wait about 40 cycles (follow spec of RTL) and check data of dbit_out | test_encode_basic_directed_data / test encode_random_data / … |  | Coverpoint |  | 100 | Directed | Hienntt87 | [5 empty] | About clock to completely decode, anldh will release about range clock to complete decode
2 | Viterbi Decoder
2.1 | Reset
2.1.1 | Reset through axi bus | Verify data in internal register return the (default value) after trigger AXI_RST_N | test_decoder_read_reg_after_reset |  | Test | 1 | 100 | Directed | Hienntt87
2.1.2 | Reset when IP is performing encode | Trigger reset entire environment when performing encode, after trigger reset, the decoder re-start follow specification | test_decoder_trigger_reset_when_encoding_data |  | Test | 100 | 100 | Constraint Random | Hienntt87
2.2 | Register
2.2.1 | Viterbi Decoder read/write internal register | Random read/write data of internal register to verify behavior RO/WO of each internal register | test_decoder_write_and_read_reg |  | Test | 1 | 100 | Constraint Random | Hienntt87
2.2.2 | Viterbi Decoder valid range address | Write random data to reserved region address of each internal register to check behavior of IP to access that region - Checkpoint: Valid address of each interal registers | test_encoder_check_valid_range_address |  | Test | 100 | 100 | Constraint Random | Hienntt87
2.3 | AXI protocol | [13 empty] | Burst read transaction over AXI are supported, but burst write transactions are not
2.3.1 | Viterbi Decoder read burst data from Dbit Out Memory | Change fields such as ARLENGTH, ARSIZE and ARBURST to verify behavior of read transaction when read data from Dbit Out Memory | viterbi_decoder_read_burst_mem_test |  | Coverpoint | 1 | 100 | Contraint Random | Hienntt87
2.3.2 | ID of both channel read and write | Change field ID when perform transaction read or write to check respones's ID |  |  | Coverpoint | 1 | 100 | Contraint Random | Hienntt87
2.4 | Viterbi Decoder Functions
2.4.1 | Operation of Viterbi Decoder | Perform normal operation of Viterbi Decoder with randomize data_in - Checkpoint: Behavior of polling status of each register in dbit_out memory to identify encode completely done or not yet - Checkpoint: Format of axi_wdata when pass data_in to decode - Checkpoint: Random AW_ID and expected B_ID return the same value - Checkpoint: Random data input with 3 ranges, low-middle-high | test_decode_basic_diredted_data / test_decode_random_data |  | Test | 1000 | 100 | Constraint Random | Hienntt87 | [5 empty] | Data_in need to be process by software before load into Viterbi Decoder
2.4.2 | Behavior of "Add-Select-Compare" block | Verify behavior of "Add-Select-Compare" block when have the same metric value (tie-break case) with input value is 96-bit all zero | test_decode_directed_all_bit_0_data |  | Test | 1 | 100 | Directed | Hienntt87 | [5 empty] | Anldh will be dicuss later
2.4.3 | Behavior of "Path Metric Caculate" block | Verify behavior of "Path Metric Caculate" block when pass input with the maximum value (all soft bit is +32), minimum value (all soft-bit is -32) or alternative +-32 to ensure the IP not overflow | test_decode_directed_all_bit_0_data / test_decode_directed_all_bit_1_data / test_decode_directed_sweep_bit_1_data / … |  | Test | 1 | 100 | Directed | Hienntt87
2.4.4 | Time to completely finish a decode process | Trigger start, wait about 40.000 cycles (follow spec of RTL) and check data of dbit_out | test_decode_basic_directed_data / test decode_random_data / … |  | Coverpoint | 1 | 100 | Directed | Hienntt87 | [5 empty] | About clock to completely decode, anldh will release about range clock to complete decode

## 6.Testlist
TESTLIST
[5 empty] | RTL |  | Pre-simulation |  | Post-simulation
No | Test name | What is checked | How to check | Priority | Started date | Finished date | Started date | Finished date | Started date | Finished date | In charge person | Note
IP Viterbi Encoder
1 | test_encoder_read_reg_after_reset | - OBJECTIVE: Check signal AXI_RST_N and default value of register - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1, random ID + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform read data of each register through axi sequence read + Compare with the default value follow specification - PASS CRITERIA: No error | Self-check | HIGH |  | 2025-09-11 |  |  |  |  | Hienntt87
2 | test_encoder_write_and_read_register | - OBJECTIVE: Check behavior RO or WO of each register - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1, random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + For DBITOUT REG, perform read the current value first, then write a random value into this register. After that, re-perform sequence axi read, check the value if it is the same or not to verify behavior RO + For others register, the value of read transaction must be different with the value of write transaction to verify behavior WO - PASS CRITERIA: No error | Self-check | NORMAL |  | 2025-10-11 |  |  |  |  | Hienntt87
3 | test_encoder_check_valid_range_address | - OBJECTIVE: Check the value of IP returned after access to reserved address, it also must be ensured that the IP is not hang out - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1, random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform constrainted random with address and data value, then write that data into that address + Perform read transactions to get value through sequence axi read + Compare with the behavior that document is mentioned (returned value must be 0) - PASS CRITERIA: No error | Self-check | LOW |  | 2025-11-11 |  |  |  |  | Hienntt87
4 | test_encode_basic_directed_data | - OBJECTIVE: Verify the entire flow of encoding process, the result have known before, it just to ensure that the flow of encoding process is correct and time to complete the encoding process is matched with time that document is mentioned - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1 ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the desired data to encode (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not + Read the result from DBITOUT register (0 -> 7) + Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | HIGH |  | 15/11/2025 |  |  |  |  | Hienntt87
5 | test_encoder_trigger_reset_when_encoding_data | - OBJECTIVE: Verify the behavior of IP Viterbi Encoder after it is triggered reset signal while processing encode data - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend peform axi read single or burst), random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the desired data to encode (DBIT register) > Trigger encoding process (START register) + After trigger start, perform generate the signal reset with the constrainted random time to reset + Re-perform encoding process with that data in + Compare the result with Model C and check if the IP is hangout or not - PASS CRITERIA: No error and IP not hangout | Scoreboard | NORMAL |  | 16/11/2025 |  |  |  |  | Hienntt87
6 | test_encode_random_data | - OBJECTIVE: Verify the entire flow of encoding process with constrained random data input, it just to ensure that the flow of encoding process is correct and time to complete the encoding process is matched with time that document is mentioned - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the desired data to encode (data just have randomized) (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C > Trigger soft reset through RST_N register > Repeat 1000 times - PASS CRITERIA: No error | Scoreboard | HIGH |  | 20/11/2025 |  |  |  |  | Hienntt87
7 | test_encode_directed_all_bit_0_data | - OBJECTIVE: Verify the behavior of block execute the XOR logic, shift bit or the position of polynomial when caculation. Furthermore, it alsao ensure the time to complete the encoding process is matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the data to encode is all 48 bits has value 0 (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 21/11/2025 |  |  |  |  | Hienntt87
8 | test_encode_directed_all_bit_1_data | - OBJECTIVE: Verify the behavior of block execute the XOR logic, shift bit or the position of polynomial when caculation. Furthermore, it alsao ensure the time to complete the encoding process is matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the data to encode is all 48 bits has value 1 (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 21/11/2025 |  |  |  |  | Hienntt87
9 | test_encode_directed_alternative_bit_1_0_data | - OBJECTIVE: Verify the behavior of block execute the XOR logic, shift bit or the position of polynomial when caculation. Furthermore, it alsao ensure the time to complete the encoding process is matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the data to encode, 48 bits has value 1 0 alternative (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 24/11/2025 |  |  |  |  | Hienntt87
10 | test_encode_directed_alternative_bit_0_1_data | - OBJECTIVE: Verify the behavior of block execute the XOR logic, shift bit or the position of polynomial when caculation. Furthermore, it alsao ensure the time to complete the encoding process is matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the data to encode, 48 bits has value 0 1 alternative (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 24/11/2025 |  |  |  |  | Hienntt87
11 | test_encode_directed_sweep_bit_0_data | - OBJECTIVE: Verify the behavior of block execute the XOR logic, shift bit or the position of polynomial when caculation. Furthermore, it alsao ensure the time to complete the encoding process is matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the data to encode, bit at position 0 has value 0, others position has value 1 (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C > Trigger soft reset through RST_N register > Repeat until the value 0 sweep all position and stop at position 47 - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 25/11/2025 |  |  |  |  | Hienntt87
12 | test_encode_directed_sweep_bit_1_data | - OBJECTIVE: Verify the behavior of block execute the XOR logic, shift bit or the position of polynomial when caculation. Furthermore, it alsao ensure the time to complete the encoding process is matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 8 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of encoding data > Perform constrained random data input > Config number bits of data in, always macro is 48 (NUM BIT register) > Config the data to encode, bit at position 0 has value 1, others position has value 0 (DBIT register) > Trigger encoding process (START register) > Polling bit at position 12 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 7) > Compare the result with Model C > Trigger soft reset through RST_N register > Repeat until the value 1 sweep all position and stop at position 47 - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 25/11/2025 |  |  |  |  | Hienntt87
IP Viterbi Decoder
1 | test_decoder_read_reg_after_reset | - OBJECTIVE: Check signal AXI_RST_N and default value of register - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1, random ID + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform read data of each register through axi sequence read + Compare with the default value follow specification - PASS CRITERIA: No error | Self-check | HIGH |  | 2025-09-11 |  |  |  |  | Hienntt87
2 | test_decoder_random_write_and_read_reg | - OBJECTIVE: Check behavior RO or WO of each register - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1, random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + For DBITOUT REG, perform read the current value first, then write a random value into this register. After that, re-perform sequence axi read, check the value if it is the same or not to verify behavior RO + For others register, the value of read transaction must be different with the value of write transaction to verify behavior WO - PASS CRITERIA: No error | Self-check | NORMAL |  | 2025-10-11 |  |  |  |  | Hienntt87
3 | test_decoder_check_valid_range_address | - OBJECTIVE: Check the value of IP returned after access to reserved address, it also must be ensured that the IP is not hang out - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1, random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform constrainted random with address and data value, then write that data into that address + Perform read transactions to get value through sequence axi read + Compare with the behavior that document is mentioned (returned value must be 0) - PASS CRITERIA: No error | Self-check | LOW |  | 2025-11-11 |  |  |  |  | Hienntt87
4 | test_decode_basic_directed_data | - OBJECTIVE: Verify the entire flow of decoding process, the result have known before, it just to ensure that the flow of decoding process is correct and time to complete the decoding process is matched with time that document is mentioned - DETAILS: + AXI protocol field: burst_type is FIXED, burst_length is 1 ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config Next State Table, load data from file into NEXT STATE TABLE register > Config Output Table, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the desired data to decode (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | HIGH |  | 2025-08-12 |  |  |  |  | Hienntt87
5 | test_decoder_trigger_reset_when_decoding_data | - OBJECTIVE: Verify the behavior of IP Viterbi Decoder after it is triggered reset signal while processing decode data - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend peform axi read single or burst, not apply for channel write), random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BIT register) > Config the desired data to decode (DBIT register) > Trigger encoding process (START register) + After trigger start, perform generate the signal reset with the constrainted random time to reset + Re-perform decoding process with that data in + Compare the result with Model C and check if the IP is hangout or not - PASS CRITERIA: No error and IP not hangout | Scoreboard | NORMAL |  | 2025-09-12 |  |  |  |  | Hienntt87
6 | test_decode_random_data | - OBJECTIVE: Verify the entire flow of decoding process with constrained random data input, it just to ensure that the flow of decoding process is correct and time to complete the decoding process is matched with time that document is mentioned - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Perform constrained random data input > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number block of data in, always macro is 1 (NUM BLOCK register) > Config the desired data to decode (data just have randomized) (DBIT register) > Trigger encoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C > Trigger soft reset through RST_N register > Repeat 1000 times - PASS CRITERIA: No error | Scoreboard | HIGH |  | 2025-11-12 |  |  |  |  | Hienntt87
7 | test_decode_data_that_is_encode_by_model_C | - OBJECTIVE: Verify the function decode of IP when the data input of IP is generated from output of model C encode, that data will follow the algorithm restrictively, and not randomly such as SystemVerilog. Furthermore, ensured that the time to complete decoding process match with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend peform axi read single or burst, not apply for channel write), random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Using model C to generate random data input and then perform encode that data by model C > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BIT register) > Config the desired data to decode, data is encoded by model C (DBIT register) > Trigger encoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare with the original value before encoding by model C > Trigger soft reset through RST_N register > Repeat 1000 times - PASS CRITERIA: No error | Self-check | NORMAL |  | 2025-10-12 |  |  |  |  | Hienntt87
8 | test_decode_directed_all_bit_0_data | - OBJECTIVE: Verify the behavior of blocks such as "Add-Select-Compare", "Path-Metric-Caculation", ... when they meet special data input and ensure that the result must be correct with no hangout, no underflow or overflow. Furthermore, the time to complete decoding process must be matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the data to decode is all 96 bits has value 0 (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 2025-12-12 |  |  |  |  | Hienntt87
9 | test_decode_directed_all_bit_1_data | - OBJECTIVE: Verify the behavior of blocks such as "Add-Select-Compare", "Path-Metric-Caculation", ... when they meet special data input and ensure that the result must be correct with no hangout, no underflow or overflow. Furthermore, the time to complete decoding process must be matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the data to decode is all 96 bits has value 1 (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 2025-12-12 |  |  |  |  | Hienntt87
10 | test_decode_directed_alternative_bit_0_1_data | - OBJECTIVE: Verify the behavior of blocks such as "Add-Select-Compare", "Path-Metric-Caculation", ... when they meet special data input and ensure that the result must be correct with no hangout, no underflow or overflow. Furthermore, the time to complete decoding process must be matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the data to decode, 96 bits has value 0 1 alternative (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 15/12/2025 |  |  |  |  | Hienntt87
11 | test_decode_directed_alternative_bit_1_0_data | - OBJECTIVE: Verify the behavior of blocks such as "Add-Select-Compare", "Path-Metric-Caculation", ... when they meet special data input and ensure that the result must be correct with no hangout, no underflow or overflow. Furthermore, the time to complete decoding process must be matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the data to decode, 96 bits has value 1 0 alternative (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 15/12/2025 |  |  |  |  | Hienntt87
12 | test_decode_directed_sweep_bit_0_data | - OBJECTIVE: Verify the behavior of blocks such as "Add-Select-Compare", "Path-Metric-Caculation", ... when they meet special data input and ensure that the result must be correct with no hangout, no underflow or overflow. Furthermore, the time to complete decoding process must be matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the data to decode, bit at position 0 has value 0 others position has value 1 (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C > Trigger soft reset through RST_N register > Repeat until value 0 sweep all positions and stop at position 95 - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 16/12/2025 |  |  |  |  | Hienntt87
13 | test_decode_directed_sweep_bit_1_data | - OBJECTIVE: Verify the behavior of blocks such as "Add-Select-Compare", "Path-Metric-Caculation", ... when they meet special data input and ensure that the result must be correct with no hangout, no underflow or overflow. Furthermore, the time to complete decoding process must be matched with number of cycles that is mentioned in document - DETAILS: + AXI protocol field: burst_type is INCR, burst_length is 1 or 48 (depend on axi read single or burst and not apply for channel write) ,random ID (both channel read and write) + Init clock and reset signal through sequences enable reset and enable clock + Trigger seuquence disable_reset + Perform the process of decoding data > Config NEXT STATE TABLE, load data from file into NEXT STATE TABLE register > Config OUTPUT TABLE, load data from file into OUTPUT TABLE register > Config number blocks of data in, always macro is 1 (NUM BLOCK register) > Config the data to decode, bit at position 0 has value 1 others position has value 0 (DBIT register) > Trigger decoding process (START register) > Polling bit at position 16 of DBIT OUT register to identify complete or not > Read the result from DBITOUT register (0 -> 47) > Compare the result with Model C > Trigger soft reset through RST_N register > Repeat until value 1 sweep all positions and stop at position 95 - PASS CRITERIA: No error | Scoreboard | NORMAL |  | 16/12/2025 |  |  |  |  | Hienntt87

## 7.Scenario_flow
SCENARIO FLOW
Definition of symbol in flowchart
Flowchart of encoding process |  |  | Flowchart of decoding process
|  | Timing diagrams illustrate for encoding process |  | Timing diagrams illustrate for decoding process
- Because the cycles to end entire of decoding process is too large (40 cycles), so it cannot illustrate on timing diagrams
Note: the cycle is end of entire encoding process is not correct follow timming diagram, it just illustrate the flow of encoding process

## 8.SVA_List
SVA List
5 | Items | Check signal | Check item | Description | Assert/Cover/Assume type | Property | assertion/cover/proterty name | Note
| Performance | SIGNAL_NAME_A0 | Connection | Ex: Check connection of SIGNAL_NAME_A0 from top module to sub-module. | Assert | p_connected | SVA_{MODULE_NAME}_{SIGNAL_NAME_A0}_{CHECK_ITEM}_{Func_ID}
|  | start, done | raise | -Check at posedge clk and not trigger reset -Check that "done" is asserted within 1-40 cycles after rising edge of "start" | Assert | start_to_done_40_cycles | assert_start_to_done_40_cycles | For encode (module Viterbi_Encode_Parallel)
|  | start, viterbi_decode_done | raise | -Check at posedge clk and not trigger reset -Check that "viterbi_decode_done" is asserted within 1-40000 cycles after rising edge of "start" | Assert | start_to_done_40000_cycles | assert_start_to_done_40000_cycles | For decode (module Viterbi_Decoder)
Interface B
Note on D5: Author: Determine the item check such as initial value, connection, pusle, rise, fall…

## 9.Q&A
Q&A
No | Date | Status | Questioner | Question | Answer | Responden by | Attached File | Remark
1 |  | Open
2 |  | Close
3 |  | Close
4 |  | Open
5 |  | Open
6 |  | Open
7 |  | Open
8 |  | Open
9 |  | Open
10 |  | Open
11 |  | Open

## 10->Appendix
NO CONTENT HERE PLEASE GO TO THE NEXT SHEETS FOR APPENDIX